Community Partner Reporting Form (TEMPLATE)

Guidance for completing this Community Partner Reporting Form:

- This reporting template should grow cumulatively over time; fill in as you go to chronicle your improvement journey

- Submit the form in the designated folder in Glasscubes

- Each cell does not need to be completed each period; only include activities/findings related to that reporting period

Agency Name: _________________________

Leader Name: _________________________

Leader Phone / Email: ___________________ / ___________________

Selected Subpopulation of Focus:

O Youth

O Transgender People

O MSM of Color

O Black/African American and Latina Women

Community Partner Aim Statement

Please insert your Aim Statement here:

<insert your aim statement>

Improvement Activities

What steps have you taken to plan and implement quality improvement activities? Please use data when possible.

| Month/Year | Describe your strategies |
| --- | --- |
|  | *Press tab for another row |

Describe your major accomplishments this reporting period.

| Month/Year | Describe your strategies |
| --- | --- |
|  | *Press tab for another row |

Describe your major challenges this reporting period.

| Month/Year | Describe your strategies |
| --- | --- |
|  | *Press tab for another row |

What are your technical assistance needs, if any, from the Collaborative Faculty or other Community Partners to move your improvement efforts forward?

| Aim# | Goal# | Month/Year | Describe your strategies |
| --- | --- | --- | --- |
|  |  |  | *Press tab for another row |

Community Partner Reporting Form (SAMPLE)

Guidance for completing this Community Partner Reporting Form:

- This reporting template should grow cumulatively over time; fill in as you go to chronicle your improvement journey

- Submit the form in the designated folder in Glasscubes

- Each cell does not need to be completed each period; only include activities/findings related to that reporting period

Agency Name: Best Care Ever

Leader Name: John Narratu

Leader Phone: 123-456-7894 / Email: jn@bestcareever.org

Selected Subpopulation of Focus:

X Youth

O Transgender People

O MSM of Color

O African American and Latina Women

Community Partner Aim Statement

Please insert your Aim Statement here:

• By Dec 2019, our Youth (13-24) subpopulation will have the same average viral suppression rate as the entire HIV caseload; no measurable disparities are detected for our Youth patients at that time

• At least 95% of Youth patients who are out of care in the past 6 months are reached out to by May 2019

• At least 85% of all HIV patients served by the agency are virally suppressed by Dec 2019 from baseline 74% in June 2018

• At least 80% of all patients served by the agency who are ART adherent but remain not virally suppressed are genotype or phenotype tested for drug resistance by Dec 2019

Improvement Activities

What steps have you taken to plan and implement quality improvement activities? Please use data when possible.

| Month/Year | Describe your strategies |
| --- | --- |
| Sep 2018 | We set up an improvement team dedicated to this QI project |
| Oct 2018 | Training for staff on mental health screening was conducted; policies for routine MH assessments were reviewed |
| Nov 2018 | We partnered with nearby sites that specialize in adolescent mental health; an MOU was developed |
| Dec 2018 | Integrating a texting program that allows staff to reach youth clients and develop the necessary staff policies |
|  | *Press tab for another row |

Describe your major accomplishments this reporting period.

| Month/Year | Describe your strategies |
| --- | --- |
| Oct 2018 | All staff were trained using our new MH assessment form; 90% of pts received a MH assessment using this form |
| Nov 2018 | The partner MH site saw the first 2 Youth pts |
| Dec 2018 | A texting program recommended by a fellow Collaborative participant was purchased |
|  | *Press tab for another row |

Describe your major challenges this reporting period.

| Month/Year | Describe your strategies |
| --- | --- |
| Sep 2018 | QI project team members are not fully trained to run the QI project |
|  | No social media outreach strategies are in place for Youth patients, such as text messaging, to remind them about upcoming appointment and stay connected between appointments |
|  | *Press tab for another row |

What are your technical assistance needs, if any, from the Collaborative Faculty or other Community Partners to move your improvement efforts forward?

| Month/Year | Describe your strategies |
| --- | --- |
| Sep 2018 | QI training is needed by the QI coach on running a QI project |
|  | Can you connect us with other agencies that have done MH screenings? Are there examples about MOUs? |
|  | *Press tab for another row |